## 说明
项目 | 内容
用途 | 按业务记录每条任务的初始 SQL（旧平台 Hive/Spark SQL）和最终跑通的 StarRocks SQL。
业务口径 | 「业务分类」列取 917 梳理 CSV 的同名列，共 22 个业务。CSV 中该列为空的行不在本表内。
初始 SQL 来源 | 大数据平台YARN上的任务梳理-云脑大数据平台-917梳理.csv「语句」列。该 CSV 首列带 * 的任务有多条 SQL，只举例一条；语句列为空或 / 的行，初始 SQL 留空。
最终 SQL 来源 | 目前只有热门威胁已记录，来自 outputs/topthreat-hot-stat-starrocks.sql（位于 cursor/sr-convert-all-sql-02a9 分支）。
状态含义 | 已跑通：用户已确认。未记录：尚未登记最终 SQL，不表示一定没有跑通，也不表示跑不通。
证据边界 | 已跑通不等于已切流。最终 SQL 里的日期和小时是实验窗口，不是生产调度参数。表和字段名按 docs/StarRocks语句转换规则.md 已确认的口径。未执行生产查询、切流或停服。
补录方法 | 在「SQL明细」把最终 SQL、状态、跑通日期、环境与证据填进对应行，再同步「业务总览」状态。重新运行 scripts/build_sql_run_record.py 默认拒绝覆盖本文件。

## 业务总览
业务 | 业务类别(CSV) | 服务 | 子任务数 | 有初始SQL的子任务数 | 已跑通子任务数 | 状态 | 备注
热门威胁-热度统计 | 热门威胁生产 | topthreat_hot_stat | 3 | 3 | 3 | 已跑通 | 三条语句（黑域名、黑文件、黑 URL）均已跑通
C2 IP情报生产-安全日志 | ip生产 | ip-security-log-etl-prc | 1 | 1 | 0 | 未记录
GPT钓鱼联动封锁-降误报 | 热度统计 | domain-heat-stats-cron-job | 3 | 3 | 0 | 未记录
aes检测 | ip生产、生产 | ti-ip-detection-send-prc、ti-hot-data-detection-fusing-prc | 2 | 2 | 0 | 未记录
mongo数据同步 | 基础设施 | sync-mongo2hive-job | 1 | 0 | 0 | 未记录
云情报网关-C段过滤 | 降误报 | filter-layout-ip-seg-stat-prc | 1 | 1 | 0 | 未记录
云情报网关-报告分析 | 运营报告 | ctig-report-data-analysis-prc | 1 | 1 | 0 | 未记录
云情报网关-数据分发 | 基础设施 | ip-intelligence-dispatch-prc、dns-intelligence-dispatch-prc、url-intelligence-dispatch-prc | 3 | 0 | 0 | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | 6 | 6 | 0 | 未记录
云情报网关监控-设备数量 | 监控 | cipd-product-resource-monitor-prc | 7 | 7 | 0 | 未记录
云鉴页面 | 云鉴 | cloud-display-manager-prc | 2 | 0 | 0 | 未记录
图数据库 | 基础设施 | ati-relations-loader-job | 4 | 0 | 0 | 未记录
图数据库-dns信息更新 | 生产 | ati-pdns-cache-job | 1 | 1 | 0 | 未记录
域名情报生产-主动降误报 | 降误报 | active-domain-elt-job | 2 | 2 | 0 | 未记录
域名情报生产-图神经网络 |  | gnn-domain-hive-query-cronjob | 1 | 1 | 0 | 未记录
域名情报生产-安全日志 | 生产 | domain-security-log-etl-prc | 2 | 2 | 0 | 未记录
域名情报生产-降误报 | 降误报 | domain-hit-devnum-cronjob | 1 | 1 | 0 | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | 5 | 5 | 0 | 未记录
情报信誉mongodb同步hive | 基础设施 | datax-server | 1 | 0 | 0 | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | 5 | 5 | 0 | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | 12 | 12 | 0 | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info(oozie)、secevent-to-hive-batch(oozie)、sodl_ods_info | 8 | 6 | 0 | 未记录

## SQL明细
业务 | 业务类别(CSV) | 服务名称 | 子任务 | 917任务类型 | 负责人 | 初始SQL（旧平台） | 最终跑通SQL（StarRocks） | 状态 | 跑通日期 | 跑通环境与证据 | 改写要点
云鉴页面 | 云鉴 | cloud-display-manager-prc | cloud-display-detail-new | 保留 | 肖扬 |  |  | 未记录
云鉴页面 | 云鉴 | cloud-display-manager-prc | cloud-display-statistic | 保留 | 肖扬 |  |  | 未记录
mongo数据同步 | 基础设施 | sync-mongo2hive-job | hashinfo-to-hive | 可下线 | 王坤 |  |  | 未记录
图数据库 | 基础设施 | ati-relations-loader-job | load_tag2hive | 保留 | 肖扬 |  |  | 未记录
图数据库 | 基础设施 | ati-relations-loader-job | load_edge2hive | 保留 | 肖扬 |  |  | 未记录
图数据库 | 基础设施 | ati-relations-loader-job | AtiRelationsLoader-iocEdges | 保留 | 肖扬 |  |  | 未记录
图数据库 | 基础设施 | ati-relations-loader-job | AtiRelationsLoader-iocTags | 保留 | 肖扬 |  |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info(oozie) | / | 保留 | 王绪寒 |  |  | 未记录
数据湖数据同步 | 基础设施 | secevent-to-hive-batch(oozie) | / | 已下线 | 王绪寒 |  |  | 未记录
域名情报生产-图神经网络 |  | gnn-domain-hive-query-cronjob | / | 保留 | 王绪寒 | SELECT DISTINCT key FROM csc.ods_csc_ioc_vertex WHERE graph_type='Domain' and atime>=1756202400 and atime<1756206000 and utime>=1755601200 and str1 in ('2','3','4') |  | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | DEVICE_STATS_SQL | 保留 | 王绪寒 | SELECT product, count(DISTINCT(dev_id)) as dev_num FROM default.ods_devicemanager_deviceinfo GROUP BY product |  | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | IP_SECURITY_SQL | 保留 | 王绪寒 | SELECT t1.threatclass as threatclass, t1.threattype as threattype, t1.threatsubtype as threatsubtype, t1.producttype as producttype, t1.url as ioc, regexp_extract(t2.customer_info, 'city=(.*?)[,}]', 1) AS city, regexp_extract(t2.customer_info, 'ip=(.*?)[,}]', 1) AS ip FROM sodl.network_security_log t1 LEFT JOIN default.ods_devicemanager_deviceinfo t2 ON t1.manage = t2.dev_id WHERE t1.reqruleid >='14000000' AND t1.reqruleid < '14999999' AND t1.titype = 2 AND t1.threatclass=209 AND t1.threattype NOT IN (9, 14, 15) AND t1.producttype != 'NULL' AND t1.manage != 'NULL' AND t1.url != 'NULL' AND t2.customer_info != 'NULL' AND t1.DAY = 20250825 AND t1.hour = 1 LIMIT 1000 |  | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | DOMAIN_SECURITY_SQL | 保留 | 王绪寒 | SELECT t1.threatclass as threatclass, t1.threattype as threattype, t1.threatsubtype as threatsubtype, t1.producttype as producttype, t1.url as ioc, regexp_extract(t2.customer_info, 'city=(.*?)[,}]', 1) AS city, regexp_extract(t2.customer_info, 'ip=(.*?)[,}]', 1) AS ip FROM sodl.network_security_log t1 LEFT JOIN default.ods_devicemanager_deviceinfo t2 ON t1.manage = t2.dev_id WHERE t1.reqruleid >='14000000' AND t1.reqruleid < '14999999' AND t1.titype = 0 AND t1.threatclass=209 AND t1.threattype NOT IN (9, 14, 15) AND t1.producttype != 'NULL' AND t1.manage != 'NULL' AND t1.url != 'NULL' AND t2.customer_info != 'NULL' AND t1.DAY = 20250825 AND t1.hour = 1 LIMIT 1000 |  | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | URL_SECURITY_SQL | 保留 | 王绪寒 | SELECT t1.threatclass as threatclass, t1.threattype as threattype, t1.threatsubtype as threatsubtype, t1.producttype as producttype, t1.url as ioc, regexp_extract(t2.customer_info, 'city=(.*?)[,}]', 1) AS city, regexp_extract(t2.customer_info, 'ip=(.*?)[,}]', 1) AS ip FROM sodl.network_security_log t1 LEFT JOIN default.ods_devicemanager_deviceinfo t2 ON t1.manage = t2.dev_id WHERE t1.reqruleid >='14000000' AND t1.reqruleid < '14999999' AND t1.titype = 1 AND t1.threatclass=214 AND t1.threattype NOT IN (2, 3) AND t1.producttype != 'NULL' AND t1.manage != 'NULL' AND t1.dstip != 'NULL' AND t1.url != 'NULL' AND t2.customer_info != 'NULL' AND t1.DAY = 20250825 AND t1.hour = 1 LIMIT 1000 |  | 未记录
情报公司大屏展示 | 运营展示 | dashboard-stats-job | FILE_SECURITY_SQL | 保留 | 王绪寒 | SELECT t1.threatclass as threatclass, t1.threattype as threattype, t1.threatsubtype as threatsubtype, t1.producttype as producttype, t1.filemd5 as ioc, regexp_extract(t2.customer_info, 'city=(.*?)[,}]', 1) AS city, regexp_extract(t2.customer_info, 'ip=(.*?)[,}]', 1) AS ip FROM sodl.endpoint_security_log t1 LEFT JOIN default.ods_devicemanager_deviceinfo t2 ON t1.manage = t2.dev_id WHERE t1.threatclass=209 AND t1.threattype NOT IN (9, 14, 15) AND t1.producttype != 'NULL' AND t1.manage != 'NULL' AND t1.filemd5 != 'NULL' AND t1.filemd5 != '' AND t2.customer_info != 'NULL' AND t1.DAY = 20250825 AND t1.hour = 1 LIMIT 1000 |  | 未记录
热门威胁-热度统计 | 热门威胁生产 | topthreat_hot_stat | blcak_file_stat | 保留 | 王绪寒 | SELECT md5, count(1)AS md5_num, count(DISTINCT devid) AS device_num FROM (SELECT lower(get_json_object(str10_tmp, "$.filemd5")) AS md5, get_json_object(str10_tmp, "$.info.attr") AS attr, str2 AS devid FROM default.log_audit_source LATERAL VIEW explode(default.format_json_list(regexp_replace(str10, '[\\\\]+"', '"'))) str10_tbl AS str10_tmp WHERE log_app_id = 'analysis-proxy-api' AND module_id IN ('file_hash' , 'file_scan') AND str1 IN ('VNGAF' , 'NGAF' , 'EDR' , 'EDR_BOTNET' , 'SIP' , 'SIP_SMTP' , 'SIP_SMB' , 'AC' , 'VAC' , 'CWPP' , 'SASE' , 'EDR_WEBSITE' , 'EDR_NPE' , 'EDR_CLOUD_IDENTIFY' , 'EDR_PK') AND long1 = 0 AND day = 20250826 AND hour = 01) a WHERE md5 IS NOT NULL AND md5 NOT IN ('', '-') AND attr='0' GROUP BY md5, devid ORDER BY md5_num DESC LIMIT 100000 | SELECT /*+ SET_VAR(new_planner_optimize_timeout = 60000) */ md5, count(1) AS md5_num, count(DISTINCT devid) AS device_num FROM (SELECT lower(get_json_object(str10_tmp, '$.filemd5')) AS md5, get_json_object(str10_tmp, '$.info.attr') AS attr, str2 AS devid FROM csc.ods_csc_log_audit, unnest(ifnull(cast(parse_json(regexp_replace(str10, '\\\\+"', '"')) AS ARRAY<JSON>), [])) AS str10_tbl(str10_tmp) WHERE app_id = 'analysis-proxy-api' AND module_id IN ('file_hash', 'file_scan') AND str1 IN ('VNGAF', 'NGAF', 'EDR', 'EDR_BOTNET', 'SIP', 'SIP_SMTP', 'SIP_SMB', 'AC', 'VAC', 'CWPP', 'SASE', 'EDR_WEBSITE', 'EDR_NPE', 'EDR_CLOUD_IDENTIFY', 'EDR_PK') AND long1 = 0 AND day = 20261001 AND hour = 0) a WHERE md5 IS NOT NULL AND md5 NOT IN ('', '-') AND attr = '0' GROUP BY md5, devid ORDER BY md5_num DESC LIMIT 100000; | 已跑通 | 2026-10-16 | 用户确认已跑通（2026-10-16）。本机实验库另执行过三条：黑域名 110 行、黑文件 0 行、黑 URL 100 行（outputs/topthreat-hot-stat-results.tsv，ACT-042）。黑文件 0 行是本机造数的 long1 不为 0，不是语句报错。 | 库表改 csc.ods_csc_log_audit（DEC-014）；log_app_id 改 app_id（DEC-015）；explode(format_json_list()) 改 unnest(parse_json())（ACT-038）；加 SET_VAR(new_planner_optimize_timeout=60000)（DEC-022）。该语句没有 sodl 分支。旧 SQL 写死 day=20250826、hour=01，新语句写 day=20261001、hour=0（实验窗口）。
热门威胁-热度统计 | 热门威胁生产 | topthreat_hot_stat | blcak_url_stat | 保留 | 王绪寒 | SELECT url, sum(url_num) AS url_num, count(DISTINCT devid) AS device_num FROM (SELECT url, devid, count(1) AS url_num FROM (SELECT lower(get_json_object(str10_tmp, "$.url")) AS url, str2 AS devid FROM default.log_audit_source LATERAL VIEW explode(default.format_json_list(regexp_replace(str10, '[\\\\]+"', '"'))) str10_tbl AS str10_tmp WHERE log_app_id IN ('url-proxy-svc' , 'cloudcheck') AND module_id IN ('url-proxy-svc' , 'CloudCheck') AND str1 IN ('VNGAF' , 'NGAF' , 'EDR' , 'EDR_BOTNET' , 'SIP' , 'SIP_SMTP' , 'SIP_SMB' , 'AC' , 'VAC' , 'CWPP' , 'SASE' , 'EDR_WEBSITE' , 'EDR_NPE' , 'EDR_CLOUD_IDENTIFY' , 'EDR_PK') AND long1 = 0 AND get_json_object(str10_tmp, "$.info.attr")='0' AND day = ${day} AND hour = ${hour} ) a WHERE url IS NOT NULL AND url NOT IN ('', '-') GROUP BY url, devid UNION ALL SELECT url, manage AS devid, sum(log_num) AS url_num FROM sodl.network_security_log WHERE url IS NOT NULL AND url NOT IN ('', '-') AND day = ${day} AND hour = ${hour} GROUP BY url, manage UNION ALL SELECT ioc AS url, manage AS devid, sum(record_count) AS url_num FROM sodl.sip_iocstat_log WHERE ioc_type = 'url' AND ioc IS NOT NULL AND ioc NOT IN ('', '-') AND day = ${day} AND hour = ${hour} GROUP BY ioc, manage ) t GROUP BY url, devid ORDER BY url_num DESC LIMIT 100000 | SELECT /*+ SET_VAR(new_planner_optimize_timeout = 60000) */ url, sum(url_num) AS url_num, count(DISTINCT devid) AS device_num FROM (SELECT url, devid, count(1) AS url_num FROM (SELECT lower(get_json_object(str10_tmp, '$.url')) AS url, str2 AS devid FROM csc.ods_csc_log_audit, unnest(ifnull(cast(parse_json(regexp_replace(str10, '\\\\+"', '"')) AS ARRAY<JSON>), [])) AS str10_tbl(str10_tmp) WHERE app_id IN ('url-proxy-svc', 'cloudcheck') AND module_id IN ('url-proxy-svc', 'CloudCheck') AND str1 IN ('VNGAF', 'NGAF', 'EDR', 'EDR_BOTNET', 'SIP', 'SIP_SMTP', 'SIP_SMB', 'AC', 'VAC', 'CWPP', 'SASE', 'EDR_WEBSITE', 'EDR_NPE', 'EDR_CLOUD_IDENTIFY', 'EDR_PK') AND long1 = 0 AND get_json_object(str10_tmp, '$.info.attr') = '0' AND day = 20261001 AND hour = 0) a WHERE url IS NOT NULL AND url NOT IN ('', '-') GROUP BY url, devid UNION ALL SELECT url, deviceId AS devid, count(1) AS url_num FROM sodl.network_security_log WHERE url IS NOT NULL AND url NOT IN ('', '-') AND insertdate = '2026-10-01' AND hour(from_unixtime(inserttimestamp)) = 0 GROUP BY url, deviceId UNION ALL SELECT ioc AS url, deviceId AS devid, sum(record_count) AS url_num FROM sodl.sip_iocstat_log WHERE ioc_type = 'url' AND ioc IS NOT NULL AND ioc NOT IN ('', '-') AND insertdate = '2026-10-01' AND hour(from_unixtime(inserttimestamp)) = 0 GROUP BY ioc, deviceId) t GROUP BY url, devid ORDER BY url_num DESC LIMIT 100000; | 已跑通 | 2026-10-16 | 用户确认已跑通（2026-10-16）。本机实验库另执行过三条：黑域名 110 行、黑文件 0 行、黑 URL 100 行（outputs/topthreat-hot-stat-results.tsv，ACT-042）。黑文件 0 行是本机造数的 long1 不为 0，不是语句报错。 | 改写项同 black_domain_stat：库表、app_id、sodl 时间条件、count(1)、deviceId、unnest(parse_json())、规划超时提示；${day}/${hour} 写死为实验窗口 20261001 / 0。
热门威胁-热度统计 | 热门威胁生产 | topthreat_hot_stat | black_domain_stat | 保留 | 王绪寒 | SELECT domain, sum(domain_num) AS domain_num, count(DISTINCT devid) AS device_num FROM (SELECT domain, devid, count(1) AS domain_num FROM (SELECT lower(get_json_object(str10_tmp, "$.domain")) AS domain, str2 AS devid FROM default.log_audit_source LATERAL VIEW explode(default.format_json_list(regexp_replace(str10, '[\\\\]+"', '"'))) str10_tbl AS str10_tmp WHERE log_app_id IN ('domain-proxy-svc' , 'cloudcheck') AND module_id IN ('domain-proxy-svc' , 'CloudCheck') AND str1 IN ('VNGAF' , 'NGAF' , 'EDR' , 'EDR_BOTNET' , 'SIP' , 'SIP_SMTP' , 'SIP_SMB' , 'AC' , 'VAC' , 'CWPP' , 'SASE' , 'EDR_WEBSITE' , 'EDR_NPE' , 'EDR_CLOUD_IDENTIFY' , 'EDR_PK') AND long1 = 0 AND get_json_object(str10_tmp, "$.info.attr")='0' AND day = ${day} AND hour = ${hour} ) a WHERE domain IS NOT NULL AND domain NOT IN ('', '-') GROUP BY domain, devid UNION ALL SELECT domain, devid, sum(log_num) AS domain_num FROM (SELECT split(split(url, '//')[size(split(url, '//')) -1], '/')[0] AS domain, MANAGE AS devid, log_num FROM sodl.network_security_log WHERE url IS NOT NULL AND url NOT IN ('', '-') AND day = ${day} AND hour = ${hour})t WHERE domain IS NOT NULL AND domain != '' GROUP BY domain, devid UNION ALL SELECT ioc AS domain, manage AS devid, sum(record_count) AS domain_num FROM sodl.sip_iocstat_log WHERE ioc_type = 'domain' AND ioc IS NOT NULL AND ioc NOT IN ('', '-') AND day = ${day} AND hour = ${hour} GROUP BY ioc, manage ) t GROUP BY domain, devid ORDER BY domain_num DESC LIMIT 100000 | SELECT /*+ SET_VAR(new_planner_optimize_timeout = 60000) */ domain, sum(domain_num) AS domain_num, count(DISTINCT devid) AS device_num FROM (SELECT domain, devid, count(1) AS domain_num FROM (SELECT lower(get_json_object(str10_tmp, '$.domain')) AS domain, str2 AS devid FROM csc.ods_csc_log_audit, unnest(ifnull(cast(parse_json(regexp_replace(str10, '\\\\+"', '"')) AS ARRAY<JSON>), [])) AS str10_tbl(str10_tmp) WHERE app_id IN ('domain-proxy-svc', 'cloudcheck') AND module_id IN ('domain-proxy-svc', 'CloudCheck') AND str1 IN ('VNGAF', 'NGAF', 'EDR', 'EDR_BOTNET', 'SIP', 'SIP_SMTP', 'SIP_SMB', 'AC', 'VAC', 'CWPP', 'SASE', 'EDR_WEBSITE', 'EDR_NPE', 'EDR_CLOUD_IDENTIFY', 'EDR_PK') AND long1 = 0 AND get_json_object(str10_tmp, '$.info.attr') = '0' AND day = 20261001 AND hour = 0) a WHERE domain IS NOT NULL AND domain NOT IN ('', '-') GROUP BY domain, devid UNION ALL SELECT domain, devid, count(1) AS domain_num FROM (SELECT split(split(url, '//')[cardinality(split(url, '//'))], '/')[1] AS domain, deviceId AS devid FROM sodl.network_security_log WHERE url IS NOT NULL AND url NOT IN ('', '-') AND insertdate = '2026-10-01' AND hour(from_unixtime(inserttimestamp)) = 0) t WHERE domain IS NOT NULL AND domain != '' GROUP BY domain, devid UNION ALL SELECT ioc AS domain, deviceId AS devid, sum(record_count) AS domain_num FROM sodl.sip_iocstat_log WHERE ioc_type = 'domain' AND ioc IS NOT NULL AND ioc NOT IN ('', '-') AND insertdate = '2026-10-01' AND hour(from_unixtime(inserttimestamp)) = 0 GROUP BY ioc, deviceId) t GROUP BY domain, devid ORDER BY domain_num DESC LIMIT 100000; | 已跑通 | 2026-10-16 | 用户确认已跑通（2026-10-16）。本机实验库另执行过三条：黑域名 110 行、黑文件 0 行、黑 URL 100 行（outputs/topthreat-hot-stat-results.tsv，ACT-042）。黑文件 0 行是本机造数的 long1 不为 0，不是语句报错。 | 库表 default.log_audit_source 改 csc.ods_csc_log_audit（DEC-014）；log_app_id 改 app_id（DEC-015）；sodl 的 day/hour 改 insertdate='2026-10-01' 与 hour(from_unixtime(inserttimestamp))=0（DEC-016/017）；sum(log_num) 改 count(1)（DEC-020）；MANAGE/manage 改 deviceId（DEC-021）；LATERAL VIEW explode(format_json_list()) 改 unnest(parse_json())，size()-1 改 cardinality()，数组下标改 1 起（ACT-038）；加 SET_VAR(new_planner_optimize_timeout=60000)（DEC-022）；${day}/${hour} 写死为实验窗口 20261001 / 0。
图数据库-dns信息更新 | 生产 | ati-pdns-cache-job | / | 保留 | 肖扬 | SELECT key AS domain FROM csc.ods_csc_ioc_vertex WHERE graph_type='Domain' AND day in {days} AND data_source NOT IN ('pdns','ngaf_dns','sip_dns') GROUP BY key |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | attack_ip_wiki_related_analysis | 保留 | 王绪寒 | SELECT "{log_name}" as table_name, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, log_num as attack_count, manage as device_id, reqruleid as sid, srcip, requesthead, requestbody, day FROM sodl.network_security_log WHERE day={day_date} AND (length(requesthead) + length(requestbody)) > {result_min_len} AND regexp_extract(srcip, "{ip_re}", 1) = "" AND (requesthead != "" OR requestbody != "") AND (regexp_extract(requesthead, "[^a-zA-Z]({filter_word})[^a-zA-Z0-9)_;,¦]") != "" OR regexp_extract(requestbody, "[^a-zA-Z]({filter_word})[^a-zA-Z0-9)_;,¦]") != "") |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | "SELECT "{log_name}" as table_name,{log_attr},day FROM {log_table_name} WHERE day={day_date} AND length(urls) > {result_min_len} AND regexp_extract(attacker_ip, "{ip_re}", 1) |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | attack_ip_af_rule_analysis | 保留 | 王绪寒 | SELECT * FROM (SELECT concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS ips, count(1) AS num FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE deleted_time=0 AND direction='1' AND expire_time>={run_time} GROUP BY concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2])) black_ip WHERE num>={segment_num} AND ips NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='attack_ip_analysis' AND part2='attack_ip_filter' ) |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | SELECT * FROM (SELECT concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS ips, count(1) AS num FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE deleted_time=0 AND direction='1' AND expire_time<{run_time} GROUP BY concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2])) black_ip WHERE num>={segment_num} AND ips NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='attack_ip_analysis' AND part2='attack_ip_filter' ) |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename,'((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id, producttype, severity FROM sodl.network_security_log WHERE DAY={day} AND concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) NOT IN ({exclude_type_list}) AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') AND regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' {low_trusted_filter}), trusted_sid_stat AS (SELECT srcip, count(distinct(reqruleid)) AS trusted_rule_count FROM {log_type} WHERE reqruleid IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_rule_id' AND (part2='high_trusted_ips_id' OR part2='high_trusted_waf_id')) GROUP BY srcip), {tag_stats}, log_stat AS (SELECT s.*, coalesce(trusted_sid_stat.trusted_rule_count, 0) AS trusted_rule_count, std.attack_std, bug_id_stat.bug_sum AS bug_sum, attack_type_stat.attack_type_sum AS attack_type_sum FROM (SELECT srcip, count(distinct(reqruleid)) AS rule_count, sum(if(log_num=0, 1, log_num)) AS attack_count, count(distinct(manage)) AS devid_count, collect_set(reqruleid) AS rule_id_list, collect_set(producttype) AS source_list, avg(severity) as avg_severity FROM {log_type} GROUP BY srcip) s LEFT JOIN trusted_sid_stat ON s.srcip = trusted_sid_stat.srcip LEFT JOIN attack_type_stat ON s.srcip = attack_type_stat.srcip LEFT JOIN bug_id_stat ON s.srcip = bug_id_stat.srcip LEFT JOIN (SELECT srcip, collect_list(reqruleid ¦¦ '@' ¦¦ attack_std) AS attack_std FROM (SELECT srcip, reqruleid, cast(stddev_pop(attack_count) AS string) AS attack_std FROM (SELECT srcip, reqruleid, manage, sum(if(log_num=0, 1, log_num)) AS attack_count FROM {log_type} GROUP BY srcip, reqruleid, manage) a GROUP BY srcip, reqruleid) b GROUP BY srcip)std ON s.srcip = std.srcip) SELECT '{log_type}' AS table_name, srcip, trusted_rule_count, rule_count, attack_count, devid_count, rule_id_list, attack_std, bug_sum, attack_type_sum, source_list, avg_severity FROM log_stat |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | WITH black_ips AS (SELECT concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS ips, count(1) AS num FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE deleted_time=0 AND direction='1' AND expire_time>={run_time} GROUP BY concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2])) SELECT ip FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE deleted_time=0 AND direction='1' AND expire_time<{run_time} AND concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) IN (SELECT ips FROM black_ips WHERE num>={segment_num}) AND concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='attack_ip_analysis' AND part2='attack_ip_filter') |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | attack_ip_af_skyeye_analysis | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename,'((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id FROM sodl.network_security_log WHERE DAY={day} AND concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) NOT IN ({exclude_type_list}) AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') AND regexp_extract(srcip,'{ip_re}') = '' AND regexp_extract(srcip,'{ipv4_re}') != '' AND cast(reqruleid AS string) NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_rule_id' AND (part2='low_trusted_ips_id' OR part2='low_trusted_waf_id'))), skyeye_ip AS (SELECT ips, count(1) AS num FROM (SELECT ip, concat(split(ip, '\\\\.')[0] , '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS ips FROM csc.ods_csc_tim_db_unknown_intelligence_tb_skyeye_ip_info_sync WHERE update_time>={skyeye_update_time} GROUP BY ip) t WHERE ips NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='attack_ip_analysis' AND part2='attack_ip_filter') GROUP BY ips), trusted_sid_stat AS (SELECT srcip, count(distinct(reqruleid)) AS trusted_rule_count FROM {log_type} WHERE reqruleid IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_rule_id' AND (part2='high_trusted_ips_id' OR part2='high_trusted_waf_id')) GROUP BY srcip), {tag_stats}, log_stat AS (SELECT s.*, coalesce(trusted_sid_stat.trusted_rule_count, 0) AS trusted_rule_count, bug_id_stat.bug_sum AS bug_sum, attack_type_stat.attack_type_sum AS attack_type_sum FROM (SELECT srcip, count(distinct(reqruleid)) AS rule_count, sum(if(log_num=0, 1, log_num)) AS attack_count, count(distinct(manage)) AS devid_count, collect_set(distinct(reqruleid)) AS rule_id_list FROM {log_type} GROUP BY srcip) s LEFT JOIN trusted_sid_stat ON s.srcip = trusted_sid_stat.srcip LEFT JOIN attack_type_stat ON s.srcip = attack_type_stat.srcip LEFT JOIN bug_id_stat ON s.srcip = bug_id_stat.srcip) SELECT * FROM log_stat WHERE concat(split(srcip, '\\\\.')[0] , '.', split(srcip, '\\\\.')[1], '.', split(srcip, '\\\\.')[2]) IN (SELECT ips FROM skyeye_ip WHERE num>={skyeye_high_num}) OR (concat(split(srcip, '\\\\.')[0] , '.', split(srcip, '\\\\.')[1], '.', split(srcip, '\\\\.')[2]) IN (SELECT ips FROM skyeye_ip WHERE num>={skyeye_num}) AND trusted_rule_count > 0) OR (srcip IN (SELECT ip FROM csc.ods_csc_tim_db_unknown_intelligence_tb_skyeye_ip_info_sync WHERE update_time>={skyeye_update_time}) AND trusted_rule_count > 0) |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | attack_ip_seclog_analysis | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename, '((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id, producttype FROM sodl.network_security_log WHERE DAY={day} AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') ), {tag_stats}, keyword_stat AS ( SELECT srcip, collect_set(keyword) AS hit_keywords FROM ( SELECT srcip, keyword FROM ( SELECT srcip, regexp_extract(requesthead, '{rce_keyword_match_sql}', 0) AS keyword FROM sodl.network_security_log where day={day} UNION SELECT srcip, regexp_extract(url, '{rce_keyword_match_sql}', 0) AS keyword FROM sodl.network_security_log where day={day} ) t WHERE keyword != '' ) t2 GROUP BY srcip ), rce_stat AS ( select keyword_stat.srcip, keyword_stat.hit_keywords, bug_id_stat.bug_sum, rule_id_stat.reqruleid_sum, attack_type_stat.attack_type_sum from keyword_stat left join bug_id_stat on keyword_stat.srcip = bug_id_stat.srcip left join rule_id_stat on keyword_stat.srcip = rule_id_stat.srcip left join attack_type_stat on keyword_stat.srcip = attack_type_stat.srcip ) SELECT '{log_type}' AS table_name, srcip, hit_keywords, bug_sum, reqruleid_sum, attack_type_sum FROM rce_stat where regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename, '((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id, regexp_extract(lower(requesthead), '(?<=user-agent: ).*?(?=\r\n)', 0) as user_agent FROM sodl.network_security_log WHERE DAY={day} and requesthead != '' and regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') ), {tag_stats}, ua_hit_record as ( select srcip, collect_set(mal_ua) AS hit_mal_ua from ( SELECT srcip, regexp_extract(user_agent, '{mal_ua_keyword_match_sql}', 0) AS mal_ua FROM {log_type} where user_agent != '') ua_agg where mal_ua != '' group by srcip ), ua_stat as ( select ua_hit_record.srcip, ua_hit_record.hit_mal_ua, bug_id_stat.bug_sum, rule_id_stat.reqruleid_sum, attack_type_stat.attack_type_sum from ua_hit_record left join bug_id_stat on ua_hit_record.srcip = bug_id_stat.srcip left join rule_id_stat on ua_hit_record.srcip = rule_id_stat.srcip left join attack_type_stat on ua_hit_record.srcip = attack_type_stat.srcip ) SELECT '{log_type}' AS table_name, srcip, hit_mal_ua, bug_sum, reqruleid_sum, attack_type_sum FROM ua_stat |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | attack_ip_low_trusted_analysis | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename,'((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id, producttype, severity FROM sodl.network_security_log WHERE DAY={day} AND concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) NOT IN ({exclude_type_list}) AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') AND regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' {low_trusted_filter}), trusted_sid_stat AS (SELECT srcip, count(distinct(reqruleid)) AS trusted_rule_count FROM {log_type} WHERE reqruleid IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_rule_id' AND (part2='high_trusted_ips_id' OR part2='high_trusted_waf_id')) GROUP BY srcip), {tag_stats}, log_stat AS (SELECT s.*, coalesce(trusted_sid_stat.trusted_rule_count, 0) AS trusted_rule_count, std.attack_std, bug_id_stat.bug_sum AS bug_sum, attack_type_stat.attack_type_sum AS attack_type_sum FROM (SELECT srcip, count(distinct(reqruleid)) AS rule_count, sum(if(log_num=0, 1, log_num)) AS attack_count, count(distinct(manage)) AS devid_count, collect_set(reqruleid) AS rule_id_list, collect_set(producttype) AS source_list, avg(severity) as avg_severity FROM {log_type} GROUP BY srcip) s LEFT JOIN trusted_sid_stat ON s.srcip = trusted_sid_stat.srcip LEFT JOIN attack_type_stat ON s.srcip = attack_type_stat.srcip LEFT JOIN bug_id_stat ON s.srcip = bug_id_stat.srcip LEFT JOIN (SELECT srcip, collect_list(reqruleid ¦¦ '@' ¦¦ attack_std) AS attack_std FROM (SELECT srcip, reqruleid, cast(stddev_pop(attack_count) AS string) AS attack_std FROM (SELECT srcip, reqruleid, manage, sum(if(log_num=0, 1, log_num)) AS attack_count FROM {log_type} GROUP BY srcip, reqruleid, manage) a GROUP BY srcip, reqruleid) b GROUP BY srcip)std ON s.srcip = std.srcip) SELECT '{log_type}' AS table_name, srcip, trusted_rule_count, rule_count, attack_count, devid_count, rule_id_list, attack_std, bug_sum, attack_type_sum, source_list, avg_severity FROM log_stat |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob | low_attack_type_ip_analysis | 保留 | 王绪寒 | WITH {log_type} AS (SELECT srcip, log_num, concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) AS attack_type, manage, reqruleid, regexp_extract(rulename,'((cve-\\\\d+-\\\\d+)¦(CVE-\\\\d+-\\\\d+)¦(cnnvd-\\\\d+-\\\\d+)¦(CNNVD-\\\\d+-\\\\d+))') AS bug_id, producttype, severity, action FROM sodl.network_security_log WHERE DAY={day} AND concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) IN ('90-5-1', '90-5-2') AND manage NOT IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_test_device_id' AND part2='attack_ip_analysis') AND regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' ), trusted_sid_stat AS (SELECT srcip, count(distinct(reqruleid)) AS trusted_rule_count FROM {log_type} WHERE reqruleid IN (SELECT str1 FROM default.ods_custom_upload_data WHERE part1='af_rule_id' AND (part2='high_trusted_ips_id' OR part2='high_trusted_waf_id')) GROUP BY srcip), {tag_stats}, log_stat AS (SELECT s.*, coalesce(trusted_sid_stat.trusted_rule_count, 0) AS trusted_rule_count, std.attack_std, bug_id_stat.bug_sum AS bug_sum, attack_type_stat.attack_type_sum AS attack_type_sum FROM (SELECT srcip, count(distinct(reqruleid)) AS rule_count, sum(if(log_num=0, 1, log_num)) AS attack_count, count(distinct(manage)) AS devid_count, collect_set(reqruleid) AS rule_id_list, collect_set(producttype) AS source_list, avg(severity) as avg_severity, collect_set(action) as action_list FROM {log_type} GROUP BY srcip) s LEFT JOIN trusted_sid_stat ON s.srcip = trusted_sid_stat.srcip LEFT JOIN attack_type_stat ON s.srcip = attack_type_stat.srcip LEFT JOIN bug_id_stat ON s.srcip = bug_id_stat.srcip LEFT JOIN (SELECT srcip, collect_list(reqruleid ¦¦ '@' ¦¦ attack_std) AS attack_std FROM (SELECT srcip, reqruleid, cast(stddev_pop(attack_count) AS string) AS attack_std FROM (SELECT srcip, reqruleid, manage, sum(if(log_num=0, 1, log_num)) AS attack_count FROM {log_type} GROUP BY srcip, reqruleid, manage) a GROUP BY srcip, reqruleid) b GROUP BY srcip)std ON s.srcip = std.srcip) SELECT '{log_type}' AS log_type, srcip as ip, trusted_rule_count, rule_count, attack_count, devid_count, rule_id_list, attack_std, bug_sum as bug_id_agg, attack_type_sum as attack_type_agg, source_list, avg_severity, action_list FROM log_stat |  | 未记录
攻击者IP情报生产 | ip生产 | attack-ip-analysis-cronjob |  | 保留 | 王绪寒 | select '{log_type}' as log_type, srcip as ip, count(distinct pwd) as pwd_num, collect_set(pwd) as pwd_list from ( SELECT srcip, regexp_extract(requesthead, '(pwd¦password)=([^&; ]+)', 2) as pwd FROM sodl.network_security_log WHERE day={day} AND regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' AND concat_ws('-',cast(threatclass as String), cast(threattype as String)) in ('94-4') and regexp_extract(requesthead, '(pwd¦password)=([^&; ]+)', 2) != '' union SELECT srcip, regexp_extract(requestbody, '(pwd¦password)=([^&; ]+)', 2) as pwd FROM sodl.network_security_log WHERE day={day} AND regexp_extract(srcip,'{private_network_pattren}') = '' AND regexp_extract(srcip,'{ipv4_pattren}') != '' AND concat_ws('-',cast(threatclass as String), cast(threattype as String)) in ('94-4') and regexp_extract(requestbody, '(pwd¦password)=([^&; ]+)', 2) != '' )a group by srcip |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | DNS_LOG_STAT_SQL | 保留 | 王绪寒 | SELECT queries as domain, sum(log_num) AS num FROM sodl.dns_log WHERE day = :date AND producttype in ('AF', 'NGAF', 'VNGAF') AND qr=0 AND length(queries) > 3 AND locate('.', queries) != 0 GROUP BY queries |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | DNS_LOG_STAT_SQL_BY_DEVICE | 保留 | 王绪寒 | SELECT queries as domain, sum(log_num) AS num FROM sodl.dns_log WHERE day = :date AND producttype in ('AF', 'NGAF', 'VNGAF') AND qr=0 AND length(queries) > 3 AND locate('.', queries) != 0 AND manage in %(devices)s GROUP BY queries |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | IP_LOG_STAT_SQL | 保留 | 王绪寒 | with ip_stat as ( SELECT concat(split(ip, '\\\\.')[0], '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS c_segment FROM (SELECT get_json_object(replace(str4, '\\\\', ''), '$[*].ip') AS ip_list FROM default.log_audit_source WHERE day = :date AND log_app_id='ip-proxy-svc' AND module_id='ip-proxy-svc' AND str1='NGAF' AND str5='[cf]') s LATERAL VIEW explode(split(regexp_replace(ip_list, '\\\\[¦\\\\]¦\\"', ''), ',')) exploded_table AS ip WHERE locate('.', ip) != 0 ) SELECT c_segment as ip, count(1) as num FROM ip_stat GROUP BY c_segment LIMIT 500000 |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | IP_LOG_STAT_SQL_BY_DEVICE | 保留 | 王绪寒 | SELECT c_segment as ip, count(1) as num FROM (SELECT concat(split(ip, '\\\\.')[0], '.', split(ip, '\\\\.')[1], '.', split(ip, '\\\\.')[2]) AS c_segment FROM (SELECT get_json_object(replace(str4, '\\\\', ''), '$[*].ip') AS ip_list FROM default.log_audit_source WHERE day = :date AND log_app_id='ip-proxy-svc' AND module_id='ip-proxy-svc' AND str1='NGAF' AND str5 = '[cf]' AND str2 in %(devices)s ) s LATERAL VIEW explode(split(regexp_replace(ip_list, '\\\\[¦\\\\]¦\\"', ''), ',')) exploded_table AS ip WHERE locate('.', ip) != 0 ) t GROUP BY c_segment LIMIT 500000 |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | URL_LOG_STAT_SQL | 保留 | 王绪寒 | SELECT host, sum(log_num) AS num FROM sodl.url_log WHERE day = :date AND host is not null AND locate('.', host) != 0 AND producttype in ('AF', 'NGAF', 'VNGAF') GROUP BY host |  | 未记录
云情报网关-过滤包生产 | 热度统计 | top-visit-host-produce-job | URL_LOG_STAT_SQL_BY_DEVICE | 保留 | 王绪寒 | SELECT host, sum(log_num) AS num FROM sodl.url_log WHERE day = :date AND host is not null AND locate('.', host) != 0 AND manage in %(devices)s AND producttype in ('AF', 'NGAF', 'VNGAF') GROUP BY host |  | 未记录
域名情报生产-降误报 | 降误报 | domain-hit-devnum-cronjob | hive_sql | 保留 | 王绪寒 | SELECT DOMAIN,devnum,total_times FROM (SELECT DOMAIN,COUNT(DISTINCT devid) AS devnum,COUNT(devid) as total_times FROM default.dwb_domain_info WHERE DAY>=20250728 and DAY<=20250827 AND devid NOT IN (SELECT str1 AS dev FROM ods_custom_upload_data WHERE part1='test_dev' AND part2='test_devid') GROUP BY DOMAIN) subquery WHERE devnum > 10 LIMIT 15000000 |  | 未记录
云情报网关-C段过滤 | 降误报 | filter-layout-ip-seg-stat-prc | hive_sql | 保留 | 王绪寒 | WITH rpt AS ( SELECT DISTINCT regexp_extract(ip, '^(\\d+\\.\\d+\\.\\d+)\\.', 1) AS ip_seg FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE direction='2' AND reputation='0' ), resp_data AS ( SELECT DAY AS date_day, split(get_json_object(resp, '$.ip'), ':')[0] AS ip, regexp_extract(split(get_json_object(resp, '$.ip'), ':')[0], '^(\\d+\\.\\d+\\.\\d+)\\.', 1) AS ip_c_seg FROM csc.ods_csc_log_audit LATERAL VIEW explode(split(replace(regexp_replace(regexp_replace(regexp_replace(str10,'^\\[',''),'~\\]',''),'\\}\,\\{','\\}\;\\{'),'\\"','"'), ';')) exploded_table AS resp WHERE app_id='ip-proxy-svc' AND DAY BETWEEN :day_min AND :day_max AND module_id='ip-proxy-svc' AND str5 RLIKE 'cf' AND get_json_object(resp, '$.threat.reputation')='2' AND get_json_object(resp, '$.threat.direction')='2' ), agg_data AS ( SELECT ip_c_seg, count(DISTINCT date_day) AS day_unique, count(DISTINCT ip) AS ip_unique, count(*)/(count(DISTINCT date_day)+1) AS total FROM resp_data GROUP BY ip_c_seg ) SELECT ip_c_seg, day_unique, ip_unique, total FROM agg_data WHERE day_unique >= :day_unique AND NOT EXISTS (SELECT 1 FROM rpt WHERE rpt.ip_seg = agg_data.ip_c_seg) |  | 未记录
域名情报生产-安全日志 | 生产 | domain-security-log-etl-prc | DOMAIN_SECURITY_LOG_EXTRACT_SQL | 保留 | 王绪寒 | SELECT DOMAIN, COLLECT_SET(producttype) AS producttype_list, COLLECT_SET(CONCAT(CAST(threatclass AS STRING), '-', CAST(threattype AS STRING), '-', CAST(threatsubtype AS STRING))) AS type_list, SORT_ARRAY(COLLECT_SET(engine)) AS engine_list, COUNT(DISTINCT engine) AS engine_num FROM (SELECT REGEXP_EXTRACT(url, '^(?:https?://)?(?:www\.)?([^/]+)', 1) AS DOMAIN, * FROM sodl.network_security_log WHERE DAY=20250826 AND engine NOT IN ('premise_ioc', 'cloud_ioc', 'sase_ioc') AND severity > 50 AND (threatclass IN (209, 208, 216, 214, 203, 40) OR CONCAT(CAST(threatclass AS STRING), '-', CAST(threattype AS STRING), '-', CAST(threatsubtype AS STRING)) = '212-10-0') AND action = 2) s WHERE NOT (DOMAIN RLIKE '\d+\.\d+\.\d+\.\d+$' OR DOMAIN RLIKE ':') GROUP BY DOMAIN |  | 未记录
域名情报生产-安全日志 | 生产 | domain-security-log-etl-prc | INFO_EXIST_CHECK_SQL | 保留 | 王绪寒 | SELECT 1 FROM sodl.network_security_log WHERE day=:mday LIMIT 1 |  | 未记录
云情报网关监控-设备数量 | 监控 | cipd-product-resource-monitor-prc | STAT_LOG_CHECK | 保留 | 王绪寒 | select 1 from csc.ods_csc_log_stats where day=:mday and app_id = 'ip-realtime-identify-etl-prc' limit 1 |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | DOMAIN_DEVICE_COUNT_STAT | 保留 | 王绪寒 | select str4, sum(long1) from csc.ods_csc_log_stats where day=:mday and app_id = 'dns-intelligence-dispatch-prc' and str1 = 'cig_subscribe' and str2 = 'dl_dns_log' group by str4 |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | CLOUDGATEWAY_IP_DEVICE_COUNT_STAT | 保留 | 王绪寒 | select str5, sum(long1) from csc.ods_csc_log_stats where day=:mday and app_id = 'ip-realtime-identify-etl-prc' and str1 = 'etl_size' and str2 = 'kafka_poll_size' and str3 = 'CLOUD_INTELLIGENCE_GATEWAY' group by str5 |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | CLOUDCHECK_IP_DEVICE_COUNT_STAT | 保留 | 王绪寒 | select str5, sum(long1) from csc.ods_csc_log_stats where day=:mday and app_id = 'ip-realtime-identify-etl-prc' and str1 = 'filter_size' and str2 = 'valid_devid' and str3 = 'CLOUDCHECK_C2IP_CF' group by str5 |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | DOMAIN_DEVICE_STAT | 保留 | 王绪寒 | select distinct str4 from csc.ods_csc_log_stats where day>=:sday and day<=:eday and app_id = 'dns-intelligence-dispatch-prc' and str1 = 'cig_subscribe' and str2 = 'dl_dns_log' |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | CLOUDGATEWAY_IP_DEVICE_STAT | 保留 | 王绪寒 | select distinct str5 from csc.ods_csc_log_stats where day>=:sday and day<=:eday and app_id = 'ip-realtime-identify-etl-prc' and str1 = 'etl_size' and str2 = 'kafka_poll_size' and str3 = 'CLOUD_INTELLIGENCE_GATEWAY' |  | 未记录
云情报网关监控-设备数量 |  | cipd-product-resource-monitor-prc | CLOUDCHECK_IP_DEVICE_STAT | 保留 | 王绪寒 | select distinct str5 from csc.ods_csc_log_stats where day>=:sday and day<=:eday and app_id = 'ip-realtime-identify-etl-prc' and str1 = 'filter_size' and str2 = 'valid_devid' and str3 = 'CLOUDCHECK_C2IP_CF' |  | 未记录
C2 IP情报生产-安全日志 | ip生产 | ip-security-log-etl-prc | / | 保留 | 王绪寒 | select distinct dstip from sodl.network_security_log where DAY=20251101 AND regexp_extract(dstip,'^((0\\.0\\.0\\.0)¦(127\\.0\\.0\\.1)¦(localhost)¦(10\\.)¦(172\\.1[6-9]\\.)¦(172\\.2[0-9]\\.)¦(172\\.3[0-1]\\.)¦(192\\.168\\.))') = '' AND regexp_extract(dstip,'^(\\d{1,3}\\.\\d{1,3}\\.\\d{1,3}\\.\\d{1,3})$') != '' AND engine not in ('premise_ioc', 'cloud_ioc', 'sase_ioc') AND severity > 50 AND (threatclass in (209, 208, 216, 214, 203, 40) or concat_ws('-',cast(threatclass as String), cast(threattype as String), cast(threatsubtype as String)) = '212-10-0') limit 100000 |  | 未记录
GPT钓鱼联动封锁-降误报 | 热度统计 | domain-heat-stats-cron-job | cloud_domain.sql | 保留 | 彭宜 | WITH t AS (SELECT DOMAIN, MANAGE, sum(log_num) AS log_sum FROM sodl.dwb_sodl_domain_info WHERE DAY =:day_str AND SUBSTRING_INDEX(DOMAIN,".",-2) in ("amazonaws.com","myqcloud.com","aliyuncs.com","myhuaweicloud.com","vercel.app","netlify.app","glitch.me","edgeone.app") GROUP BY DOMAIN, MANAGE) SELECT domain, sum(log_sum) AS log_cnt, count(DISTINCT MANAGE) AS dev_cnt FROM t GROUP BY domain |  | 未记录
GPT钓鱼联动封锁-降误报 | 热度统计 | domain-heat-stats-cron-job | second_level_domain.sql | 保留 | 彭宜 | WITH t AS (SELECT DOMAIN, MANAGE, sum(log_num) AS log_num FROM sodl.dwb_sodl_domain_info WHERE DAY =:day_str AND DOMAIN != '' AND locate(":",DOMAIN) == 0 AND locate("_",DOMAIN) == 0 AND locate("*",DOMAIN) == 0 AND DOMAIN NOT rlike "[0-9]$" AND DOMAIN NOT rlike ".arpa$" GROUP BY DOMAIN, MANAGE), t2 AS (SELECT SUBSTRING_INDEX(DOMAIN,".",-2) AS sld, sum(log_num) AS log_sum, count(DISTINCT MANAGE) AS dev_cnt FROM t GROUP BY SUBSTRING_INDEX(DOMAIN,".",-2)) SELECT sld AS domain, log_sum AS log_cnt, dev_cnt FROM t2 where log_sum >10 |  | 未记录
GPT钓鱼联动封锁-降误报 | 热度统计 | domain-heat-stats-cron-job | third_level_domain.sql | 保留 | 彭宜 | WITH t AS (SELECT DOMAIN, MANAGE, sum(log_num) AS log_num FROM sodl.dwb_sodl_domain_info WHERE DAY =:day_str AND SUBSTRING_INDEX(DOMAIN,".",-2) in ("com.cn","org.cn") GROUP BY DOMAIN, MANAGE), t2 AS (SELECT SUBSTRING_INDEX(DOMAIN,".",-3) AS parent_domain, sum(log_num) AS log_sum, count(DISTINCT MANAGE) AS dev_cnt FROM t GROUP BY SUBSTRING_INDEX(DOMAIN,".",-3)) SELECT parent_domain AS domain, log_sum AS log_cnt, dev_cnt FROM t2 where log_sum >10 |  | 未记录
情报信誉mongodb同步hive | 基础设施 | datax-server | / | 可下线 | 王绪寒 |  |  | 未记录
aes检测 | ip生产 | ti-ip-detection-send-prc | SQL | 待确认 | 肖扬 | SELECT DISTINCT splitByChar(':', JSONExtractString(element, 'ip'))[1] AS ip_address, splitByChar(':', JSONExtractString(element, 'ip'))[2] AS port FROM sodl.operation_rdp_event_log ARRAY JOIN JSONExtractArrayRaw(businessContent) AS element WHERE businessType = '21' AND formatDateTime(toDateTime(insertTimestamp), '%%Y%%m%%d%%H') >= '%s' AND formatDateTime(toDateTime(insertTimestamp), '%%Y%%m%%d%%H') < '%s' limit %d; |  | 未记录
aes检测 | 生产 | ti-hot-data-detection-fusing-prc | SQL | 待确认 | 肖扬 | SELECT fileMd5, deviceId, virusName FROM sodl.handle_info_log WHERE formatDateTime(toDateTime(insertTimestamp), '%Y%m%d%H') >= '{}' AND formatDateTime(toDateTime(insertTimestamp), '%Y%m%d%H') < '{}' AND engineInfo LIKE '%IsHotspot%' AND detectEngine = '4' |  | 未记录
云情报网关-报告分析 | 运营报告 | ctig-report-data-analysis-prc | STAT_SQL | 保留 | 王绪寒 | WITH black_reputation_domain as( SELECT domain, concat_ws( '¦', regexp_extract(labels, 'category=([^,}}]+)', 1), regexp_extract(labels, 'family=([^,}}]+)', 1) )as label, threat_level, add_time, update_time FROM csc.ods_csc_db_domain_intelligence_tb_domain_reputation_sync WHERE reputation = '0' AND deleted_time = 0 ), black_reputation_ip as( SELECT ip, concat_ws( '¦', regexp_extract(labels, 'category=([^,}}]+)', 1), regexp_extract(labels, 'family=([^,}}]+)', 1) )as label, threat_level, add_time, update_time FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE reputation = '0' AND direction='2' AND port=0 AND deleted_time=0 ), tenant_info as( SELECT DISTINCT t.tenant_id, t.device_id, d.device_id_encryption FROM csc.ods_csc_tb_tenant_subscribe_info t LATERAL VIEW OUTER explode(split(t.device_id_encryption, ',')) d AS device_id_encryption where tenant_id in ({tenant_ids}) ), domain_filtered_log as( select tenant_info.tenant_id, tenant_info.device_id, log_info.day, log_info.srcip, log_info.domain as ioc, sum(log_info.log_num) as log_num, black_reputation_domain.add_time, black_reputation_domain.label, black_reputation_domain.threat_level from ( SELECT day, srcip, manage as device_id, domain, log_num, row_key FROM sodl.dwb_sodl_domain_info WHERE day BETWEEN {start_time} and {end_time} and row_key != '' -- 云情报网关日志 and producttype = 'AF' and src_log = 'network_security_log' and reqruleid BETWEEN '140000000' AND '149999999' ) log_info JOIN tenant_info ON log_info.device_id = tenant_info.device_id_encryption JOIN black_reputation_domain ON black_reputation_domain.domain = log_info.row_key group by tenant_info.tenant_id, tenant_info.device_id, log_info.day, log_info.srcip, log_info.domain, black_reputation_domain.add_time, black_reputation_domain.label, black_reputation_domain.threat_level ), ip_filtered_log as( select tenant_info.tenant_id, tenant_info.device_id, log_info.day, log_info.srcip, log_info.dstip as ioc, sum(log_info.log_num) as log_num, black_reputation_ip.add_time, black_reputation_ip.label, black_reputation_ip.threat_level from ( SELECT day, srcip, manage as device_id, dstip, log_num FROM sodl.dwb_sodl_ip_info WHERE day BETWEEN {start_time} and {end_time} -- 云情报网关日志 and producttype = 'AF' and src_log = 'network_security_log' and reqruleid BETWEEN '140000000' AND '149999999' -- 排除非法IP and dstip !='' and dstip not in ('8.8.8.8', '8.8.4.4','114.114.114.114', '114.114.115.115', '119.29.29.29', '223.5.5.5', '223.6.6.6', '1.1.1.1', '1.0.0.1') and dstip RLIKE '^([0-9]{{1,3}}\\\.){{3}}[0-9]{{1,3}}$' and dstip NOT RLIKE '^(0\\\.¦127\\\.¦10\\\.¦172\\\.(1[6-9]¦2[0-9]¦3[01])\\\.¦192\\\.168\\\.)' ) log_info JOIN tenant_info ON log_info.device_id = tenant_info.device_id_encryption JOIN black_reputation_ip ON black_reputation_ip.ip = log_info.dstip group by tenant_info.tenant_id, tenant_info.device_id, log_info.day, log_info.srcip, log_info.dstip, black_reputation_ip.add_time, black_reputation_ip.label, black_reputation_ip.threat_level ), data_stat AS( SELECT * FROM domain_filtered_log union all SELECT * FROM ip_filtered_log ), ip_rpt_update_stat as( SELECT count(1) as rpt_update_num FROM black_reputation_ip WHERE update_time > CAST(unix_timestamp('{start_time}', 'yyyyMMdd') * 1000 AS BIGINT) ), domain_rpt_update_stat as( SELECT count(1) as rpt_update_num FROM black_reputation_domain WHERE update_time > CAST(unix_timestamp('{start_time}', 'yyyyMMdd') * 1000 AS BIGINT) ), url_rpt_update_stat as( SELECT count(1) as rpt_update_num FROM csc.ods_csc_db_url_intelligence_tb_url_reputation_sync WHERE update_time > CAST(unix_timestamp('{start_time}', 'yyyyMMdd') * 1000 AS BIGINT) and deleted_time=0 and scene='malice' ), file_rpt_update_stat as( SELECT count(1) as rpt_update_num FROM sri.ods_sri_hashinfo WHERE CAST(regexp_extract(update_time, '\\\:\\\s*([0-9]+)', 1) AS BIGINT) > CAST(unix_timestamp('{start_time}', 'yyyyMMdd') * 1000 AS BIGINT) ), day_stat as( select tenant_id, day, sum(log_num) as log_num from data_stat group by tenant_id, day ), log_stat as( select tenant_id, srcip, device_id, ioc, sum(log_num) as log_num, add_time, label, threat_level from data_stat group by tenant_id, srcip, device_id, ioc, add_time, label, threat_level ) select t1.tenant_id, t3.rpt_update_num, t2.log_stat_arr, t1.day_stat_arr from ( select tenant_id, collect_list(concat_ws(',', cast(day as string), cast(log_num as string))) AS day_stat_arr from day_stat group by tenant_id ) t1 join ( select tenant_id, collect_list( concat_ws(',',srcip,device_id, ioc,cast(log_num as string),cast(add_time as string),label,threat_level) )as log_stat_arr from log_stat group by tenant_id )t2 on t1.tenant_id = t2.tenant_id cross join ( select (ip_rpt_update_stat.rpt_update_num + domain_rpt_update_stat.rpt_update_num + url_rpt_update_stat.rpt_update_num + file_rpt_update_stat.rpt_update_num) as rpt_update_num from ip_rpt_update_stat, domain_rpt_update_stat, url_rpt_update_stat, file_rpt_update_stat limit 1 ) t3 |  | 未记录
域名情报生产-主动降误报 | 降误报 | active-domain-elt-job | INFO_EXIST_CHECK_SQL | 保留 | 王绪寒 | WITH black_dns AS ( SELECT domain, regexp_extract(labels, 'category=([^,]+)', 1) AS category, regexp_extract(labels, 'family=([^,]+)', 1) AS family, regexp_extract(label_details, 'source=([^,]+)', 1) AS source, regexp_extract(label_details, 'rule=([^,]+)', 1) AS rule, add_time AS addtime FROM csc.ods_csc_db_domain_intelligence_tb_domain_reputation_sync WHERE deleted_time=0 AND reputation='0'), test_dev AS ( SELECT str1 AS dev1 FROM default.ods_custom_upload_data WHERE part1='test_dev' AND part2='test_devid') SELECT blackdns, addtime, category, family, source, rule, count(DISTINCT dev) AS devcn FROM (SELECT a.row_key AS blackdns, b.addtime, b.category, b.family, b.source, b.rule, a.manage AS dev FROM sodl.dwb_sodl_domain_info a JOIN black_dns b ON (a.row_key=b.domain) WHERE a.day=:start_day AND a.row_key IS NOT NULL AND a.manage NOT IN (SELECT * FROM test_dev) UNION ALL SELECT a.row_key AS blackdns, b.addtime, b.category, b.family, b.source, b.rule, a.devid AS dev FROM default.dwb_domain_info a JOIN black_dns b ON (a.row_key=b.domain) WHERE a.day=:start_day AND a.row_key IS NOT NULL AND a.devid NOT IN (SELECT * FROM test_dev) )t GROUP BY blackdns, addtime, category, family, source, rule |  | 未记录
域名情报生产-主动降误报 | 降误报 | active-domain-elt-job | ACTIVE_DOMAIN_SQL | 保留 | 王绪寒 | "dwb_domain_info": """SELECT 1 FROM default.dwb_domain_info WHERE day=:mday LIMIT 1""", "dwb_sodl_domain_info": """SELECT 1 FROM sodl.dwb_sodl_domain_info WHERE day=:mday LIMIT 1""" |  | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | C2_IP_ACTIVE_STAT_SQL | 保留 | 王绪寒 | WITH reputation_ip_stat AS (SELECT ip, port, direction, expire_time, deleted_time, attack_count, devid, "其他" as industry, "其他" as country, "其他" as province, src_log FROM ( SELECT ip, port, direction, expire_time, deleted_time FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE direction="2" AND port=0 ) black_reputation_ip JOIN (SELECT sum(attack_count) as attack_count, MANAGE AS devid, COALESCE(CAST(threatclass AS STRING), '0') AS src_log, dstip AS dip FROM sodl.dwb_sodl_ip_info WHERE DAY=:mday and src_log in ('sip_iocstat_log', 'network_security_log') and dstip !='' and dstip not in ('8.8.8.8', '8.8.4.4','114.114.114.114', '114.114.115.115', '119.29.29.29', '223.5.5.5', '223.6.6.6', '1.1.1.1', '1.0.0.1') and regexp_extract(dstip,'^(\\\d{1,3}\\\.\\\d{1,3}\\\.\\\d{1,3}\\\.\\\d{1,3})$') != '' and regexp_extract(dstip, '^(0\\\.¦127\\\.¦10\\\.¦172\\\.1[6-9]\\\.¦172\\\.2[0-9]\\\.¦172\\\.3[01]\\\.¦192\\\.168\\\.¦169\\\.254\\\.¦192\\\.0\\\.0\\\.¦192\\\.88\\\.99\\\.¦198\\\.18\\\.¦198\\\.19\\\.¦198\\\.51\\\.100\\\.¦203\\\.0\\\.113\\\.¦224\\\.¦240\\\.¦255\\\.)') = '' group by dstip, MANAGE, threatclass ) b ON black_reputation_ip.ip=b.dip ), industry_stats AS ( SELECT ip, industry, SUM(attack_count) AS industry_attack_count FROM reputation_ip_stat GROUP BY ip, industry ), region_stats AS ( SELECT ip, country, province, SUM(attack_count) AS region_attack_count FROM reputation_ip_stat GROUP BY ip, country, province ), log_stats AS ( SELECT ip, src_log, SUM(attack_count) AS log_attack_count FROM reputation_ip_stat GROUP BY ip, src_log ) SELECT ris.ip, ris.port, ris.direction, ris.expire_time, ris.deleted_time, SUM(ris.attack_count) AS attack_count, COLLECT_set(CONCAT(ris.devid)) AS devids, COLLECT_set(CONCAT(ris.industry, '@', ins.industry_attack_count)) AS industry_count, COLLECT_set(CONCAT(ris.country, '@', ris.province, '@', rs.region_attack_count)) AS region_count, COLLECT_set(CONCAT(ris.src_log, '@', ls.log_attack_count)) AS src_log_count FROM reputation_ip_stat ris JOIN industry_stats ins ON ris.ip=ins.ip AND ris.industry=ins.industry JOIN region_stats rs ON ris.ip=rs.ip AND ris.country=rs.country AND ris.province=rs.province JOIN log_stats ls ON ris.ip=ls.ip AND ris.src_log=ls.src_log GROUP BY ris.ip, ris.port, ris.direction, ris.expire_time, ris.deleted_time |  | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | ATTACK_IP_ACTIVE_STAT_SQL | 保留 | 王绪寒 | WITH black_reputation_ip AS ( SELECT ip, port, direction, expire_time, deleted_time FROM csc.ods_csc_tim_db_intelligence_tb_ip_reputation_sync WHERE direction="1" AND port=0 ), reputation_ip_stat AS (SELECT ip, port, direction, expire_time, deleted_time, attack_count, devid, industry, country, province, src_log FROM black_reputation_ip JOIN (SELECT attack_count, MANAGE AS devid, CASE WHEN industry IS NULL OR length(industry) = 0 THEN "其他" ELSE industry END AS industry, CASE WHEN country IS NULL OR length(country) = 0 THEN "其他" ELSE country END AS country, CASE WHEN province IS NULL OR length(province) = 0 THEN "其他" ELSE province END AS province, COALESCE(CAST(threatclass AS STRING), '0') AS src_log, srcip AS sip FROM sodl.dwb_sodl_ip_info WHERE DAY=:mday ) b ON black_reputation_ip.ip=b.sip ) SELECT ip, port, direction, expire_time, deleted_time, attack_count, devids, industry_count, region_count, src_log_count FROM (SELECT ip, port, direction, expire_time, deleted_time, SUM(attack_count) AS attack_count, COLLECT_set(CONCAT(devid)) AS devids, COLLECT_set(CONCAT(industry, '@', industry_attack_count)) AS industry_count, COLLECT_set(CONCAT(country, '@', province, '@', region_attack_count)) AS region_count, COLLECT_set(CONCAT(src_log, '@', log_attack_count)) AS src_log_count FROM (SELECT ip, port, direction, expire_time, deleted_time, attack_count, devid, industry, country, province, src_log, SUM(attack_count) OVER (PARTITION BY ip, industry) AS industry_attack_count, SUM(attack_count) OVER (PARTITION BY ip, country, province) AS region_attack_count, SUM(attack_count) OVER (PARTITION BY ip, src_log) AS log_attack_count FROM reputation_ip_stat) t GROUP BY ip, port, direction, expire_time, deleted_time) b |  | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | DOMAIN_ACTIVE_STAT_SQL | 保留 | 王绪寒 | WITH domain_stat AS (SELECT black_reputation_domain.domain, black_reputation_domain.deleted_time, attack_count, devid, "其他" as industry, "其他" as country, "其他" as province, src_log FROM ( SELECT domain, deleted_time FROM csc.ods_csc_db_domain_intelligence_tb_domain_reputation_sync where reputation = '0' ) black_reputation_domain JOIN (SELECT sum(attack_count) as attack_count, MANAGE AS devid, COALESCE(CAST(threatclass AS STRING), '0') AS src_log, domain FROM sodl.dwb_sodl_domain_info WHERE DAY=:mday and row_key!='' group by domain, MANAGE, threatclass ) b ON black_reputation_domain.domain=b.domain ), industry_stats AS ( SELECT domain, industry, SUM(attack_count) AS industry_attack_count FROM domain_stat GROUP BY domain, industry ), region_stats AS ( SELECT domain, country, province, SUM(attack_count) AS region_attack_count FROM domain_stat GROUP BY domain, country, province ), log_stats AS ( SELECT domain, src_log, SUM(attack_count) AS log_attack_count FROM domain_stat GROUP BY domain, src_log ) SELECT ds.domain, ds.deleted_time, SUM(ds.attack_count) AS attack_count, COLLECT_set(CONCAT(ds.devid)) AS devids, COLLECT_set(CONCAT(ds.industry, '@', ins.industry_attack_count)) AS industry_count, COLLECT_set(CONCAT(ds.country, '@', ds.province, '@', rs.region_attack_count)) AS region_count, COLLECT_set(CONCAT(ds.src_log, '@', ls.log_attack_count)) AS src_log_count FROM domain_stat ds JOIN industry_stats ins ON ds.domain=ins.domain AND ds.industry=ins.industry JOIN region_stats rs ON ds.domain=rs.domain AND ds.country=rs.country AND ds.province=rs.province JOIN log_stats ls ON ds.domain=ls.domain AND ds.src_log=ls.src_log GROUP BY ds.domain, ds.deleted_time |  | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | MD5_ACTIVE_STAT_SQL | 保留 | 王绪寒 | WITH md5_stat AS (SELECT filehash AS md5, manage AS devid, attack_count, industry, country, province FROM sodl.dwb_sodl_md5_info WHERE src_log='endpoint_security_log' AND file_attr='0' AND DAY=:mday UNION ALL SELECT md5, devid, attack_count, industry, country, province FROM default.dwb_md5_info WHERE src_log='log_audit' AND SOURCE='file_hash' AND attr='0' AND DAY=:mday) SELECT base_stat.md5, base_stat.attack_count, base_stat.devids, industry_count, region_count FROM (SELECT md5, sum(attack_count) AS attack_count, collect_list(concat(devid)) AS devids FROM md5_stat GROUP BY md5) base_stat JOIN (SELECT md5, collect_list(concat(industry, '@', attack_count)) AS industry_count FROM (SELECT md5, CASE WHEN industry IS NULL OR length(industry) = 0 THEN "其他" ELSE industry END AS industry, sum(attack_count) AS attack_count FROM md5_stat GROUP BY md5, industry) industry_temp GROUP BY md5) industry_stat ON base_stat.md5 = industry_stat.md5 JOIN (SELECT md5, collect_list(concat(country, '@', province, '@', attack_count)) AS region_count FROM (SELECT md5, CASE WHEN country IS NULL OR length(country) = 0 THEN "其他" ELSE country END AS country, CASE WHEN province IS NULL OR length(province) = 0 THEN "其他" ELSE province END AS province, sum(attack_count) AS attack_count FROM md5_stat GROUP BY md5, country, province) region_temp GROUP BY md5) region_stat ON base_stat.md5 = region_stat.md5 |  | 未记录
情报上下文-攻击次数统计 | 上下文生产 | black-ti-context-produce-prc | INFO_EXIST_CHECK_SQL | 保留 | 王绪寒 | SELECT 1 FROM sodl.dwb_sodl_domain_info WHERE day=:mday LIMIT 1 SELECT 1 FROM sodl.dwb_sodl_ip_info WHERE day=:mday LIMIT 1 SELECT count(1) FROM (SELECT 1 FROM sodl.dwb_sodl_md5_info WHERE src_log='endpoint_security_log' AND file_attr='0' AND DAY=:mday LIMIT 1) t LIMIT 1 SELECT count(1) FROM (SELECT 1 FROM default.dwb_md5_info WHERE src_log='log_audit' AND SOURCE='file_hash' AND attr='0' AND DAY=:mday LIMIT 1) t LIMIT 1 |  | 未记录
云情报网关-数据分发 | 基础设施 | ip-intelligence-dispatch-prc | ti-unknown-ipdata-consume scia/default/collect-ngaf-ipdata-log | 保留 | 王绪寒 |  |  | 未记录
云情报网关-数据分发 | 基础设施 | dns-intelligence-dispatch-prc | ti-unknown-dns-consume scia/default/dns_log | 保留 | 王绪寒 |  |  | 未记录
云情报网关-数据分发 | 基础设施 | url-intelligence-dispatch-prc | ti-unknown-url-consume scia/default/collect-ngaf-url-log | 保留 | 王绪寒 |  |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | dns_log.sql | 保留 | 王绪寒 | select productType, manage, productVer, srcIp, dstIp, qr, qTypes, queries, aTypes, answers, count(1) as log_num from sodl.dns_log where insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') and insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') group by productType, manage, productVer, srcIp, dstIp, qr, qTypes, queries, aTypes, answers FORMAT Parquet settings max_memory_usage=21474836480 |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | endpoint_security_log.sql | 保留 | 王绪寒 | select threatClass, threatType, threatSubType, productType, manage, manageIp, productVer, engine, fileMd5, domain, count(1) as log_num from sodl.endpoint_security_log where insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') and insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') group by threatClass, threatType, threatSubType, productType, manage, manageIp, productVer, engine, fileMd5, domain FORMAT Parquet settings max_memory_usage=21474836480 |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | http_log.sql | 保留 | 王绪寒 | SELECT productType, manage, productVer, srcIp, dstIp, url, count(1) AS log_num FROM sodl.http_log WHERE insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') AND insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') AND productType IN ('NGAF', 'AF', 'VNGAF') GROUP BY productType, manage, productVer, srcIp, dstIp, url FORMAT Parquet settings max_memory_usage = 21474836480 |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | network_security_log.sql | 保留 | 王绪寒 | select threatClass, threatType, threatSubType, productType, manage, productVer, srcIp, dstIp, reqRuleId, -- sid fileHash, action, -- waf, ips -> net_atcion tiType, riskLevel, -- sip_filethreat_result -> threat severity, -- waf, ips -> level engine, url, result, count(1) as log_num, ruleName, requestHead, requestBody from sodl.network_security_log where insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') and insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') group by threatClass, threatType, threatSubType, productType, manage, productVer, srcIp, dstIp, reqRuleId, -- sid fileHash, action, -- waf, ips -> net_atcion tiType, riskLevel, -- sip_filethreat_result -> threat severity, -- waf, ips -> level engine, url, result, ruleName, requestHead, requestBody FORMAT Parquet settings max_memory_usage=21474836480 |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | sip_iocstat_log.sql | 保留 | 王绪寒 | select productType, deviceId as manage, productVer, ioc_type, ioc, sum(record_count) as record_count, count(1) as log_num from sodl.sip_iocstat_log where insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') and insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') group by productType, deviceId, productVer, ioc_type, ioc FORMAT Parquet settings max_memory_usage = 21474836480 |  | 未记录
数据湖数据同步 | 基础设施 | sodl_ods_info | url_log.sql | 保留 | 王绪寒 | select productType, deviceId as manage, productVer, sip, dip, host, uri, urls, count(1) as log_num from sodl.url_log where insertTimestamp >= toUnixTimestamp('{start_time}', 'Asia/Shanghai') and insertTimestamp < toUnixTimestamp('{end_time}', 'Asia/Shanghai') group by productType, deviceId, productVer, sip, dip, host, uri, urls FORMAT Parquet settings max_memory_usage = 21474836480 |  | 未记录